## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | SM/14194 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 758/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 7.79 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | SM/14194 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR BHALUKHOP KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK-KALIMPONG-I, DISTRICT-KALIMPONG. |  |  | ORD/000054/2023-2024 | 672/NKWSMD | 12/07/2023 | 06/02/2025 | SRINIWAS AGARWAL | 678.82 | 0 | 0 | 70
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | SM/14194 | New | Leftout Scheme Proposed Gravity Based Piped Water Supply Scheme for Bhalukhop Khasmahal under Kalimpong Block-I District-Kalimpong. |  |  | ORD/000132/2024-2025 | 2231/NKWSMD | 09/12/2024 | 09/03/2025 | SRINIWAS AGARWAL | 53.33 | 0 | 0 | 0
Total | [13 empty] | 739.94 | 0 | 0