## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | SM/15463 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | Assistant Engineer II | Junior Engineer III | ORD/000327/2022-2023 | 2660/NKWSMD | 28/02/2023 | 22/06/2024 | THUPDEN BHUTIA | 200.56 | 174.65 | 87.08 | 97
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | SM/15463 | New | Material Requisition To Resource Division |  |  | RTOR000256/2022-2023 | 2774/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 1.02 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | SM/15463 | New | Material Requisition To Resource Division |  |  | RTOR000247/2022-2023 | 2709/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 1.02 | 0 | 0 | 0
Total | [13 empty] | 202.59 | 174.65 | 86.21