## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | SM/15554 | New | Material Requisition To Resource Division |  |  | RTOR000251/2022-2023 | 2749/NKWSMD | 06/03/2023 | 06/03/2023 | Resource Division | 0.86 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | SM/15554 | New | KUMAI FOREST(PART) & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/016058) |  |  | ORD/000335/2022-2023 | 2731/NKWSMD | 03/03/2023 | 30/08/2023 | PUSHPA KUMAR RIZAL | 195.31 | 108.88 | 55.75 | 50
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | SM/15554 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer II ,Junior Engineer IV | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 197.12 | 108.88 | 55.23