## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 | New | Material Requisition To Resource Division |  |  | RTOR000255/2022-2023 | 2775/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 4.22 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 | New | Material Requisition To Resource Division |  |  | RTOR000246/2022-2023 | 2710/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 4.22 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000326/2022-2023 | 2659/NKWSMD | 28/02/2023 | 17/02/2025 | M/S. ASHOK KUMAR PERIWAL | 474.98 | 0 | 0 | 90
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 | New | Demand note for Proposal of Diversion of 0.03917 ha of forest land for Gravity Based Water supply scheme for Teesta DIF fund by West Bengal Public Health Engineering Directorate under Jal Jeevan Mission. |  |  | BILL/00234/2024-2025 | BP-2024-25-221 | 28/08/2024 | 28/08/2024 | WBSFDA | 1.76 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 | New | Demand note for proposal of Diversion of 0.03917 ha of forest land for Gravity based water supply scheme for Teesta DIF fund by West Bengal Public Health Engineering Directorate under Jal Jeevan mission. |  |  | BILL/00233/2024-2025 | BP-2024-25-222 | 28/08/2024 | 28/08/2024 | WBSFDA | 2.6 | 0 | 0 | 0
Total | [13 empty] | 487.78 | 0 | 0