## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15641 | New | Material Requisition To Resource Division |  |  | RTOR000249/2022-2023 | 2722/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 1.69 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15641 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 25/12/2023 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15641 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15641 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT: KALIMPONG |  |  | ORD/000329/2022-2023 | 2668/NKWSMD | 28/02/2023 | 17/02/2025 | DIPESH RAI | 202.99 | 140.73 | 69.33 | 90
Total | [13 empty] | 221.74 | 140.73 | 63.46