## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15642 | New | Material Requisition To Resource Division |  |  | RTOR000243/2022-2023 | 2718/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 96.35 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15642 | New | Proposed Pumping based Piped water supply scheme for Rambi Bazar DIF under Teesta G.P. Kalimpong Block I District Kalimpong. |  |  | BILL/00423/2024-2025 |  | 26/09/2024 | 26/09/2024 | WBSEDCL | 5.15 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15642 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00958/2023-2024 | BP-2023-24-655 | 23/03/2024 | 23/03/2024 | WBSEDCL | 5.15 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15642 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 142.95 | 79.56 | 80
Total | [13 empty] | 286.35 | 142.95 | 49.92