## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | SM/15643 | New | Material Requisition To Resource Division |  |  | RTOR000244/2022-2023 | 2719/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 1.04 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | SM/15643 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHAS MAHAL UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG |  |  | ORD/000323/2022-2023 | 2653/NKWSMD | 28/02/2023 | 27/08/2023 | MS. SURYA I PVT. LTD COMPANY | 283.56 | 48.06 | 16.95 | 70
Total | [13 empty] | 284.6 | 48.06 | 16.89