## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15644 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 246/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 3.31 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15644 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15644 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. |  |  | ORD/000039/2023-2024 | 222/NKWSMD | 10/05/2023 | 18/02/2026 | SITA SHARMA | 625.46 | 0 | 0 | 50
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15644 | New | Demand note for payment for Boundary pillars of the diverted forest land against proposed 0.0271 ha land to be diverted Jal Jeevan Mission. (Memo No. 855/9-57/441235, Dated, Kalimpong, the 20.03.2025) |  |  | BILL/00017/2025-2026 | 82/NK/C/W/FORES | 11/07/2025 | 11/07/2025 | DIVISIONAL FOREST OFFICER | 0.62 | 0 | 0 | 0
Total | [13 empty] | 646.11 | 0 | 0