## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15645 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 250/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 2.99 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15645 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT : KALIMPONG. |  |  | ORD/000037/2023-2024 | 220/NKWSMD | 10/05/2023 | 05/11/2024 | SRINIWAS AGARWAL | 940.34 | 0 | 0 | 85
Total | [13 empty] | 943.34 | 0 | 0