## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/15646 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PALLA KHASMAHAL(MULPALA PART) UNDER LOLAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG |  |  | ORD/000328/2022-2023 | 2662/NKWSMD | 28/02/2023 | 26/10/2023 | SRINIWAS AGARWAL | 197.88 | 87.32 | 44.13 | 50
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/15646 | New | Material Requisition To Resource Division |  |  | RTOR000248/2022-2023 | 2721/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 1.05 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/15646 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-II, P.H.E.D., GTA. | Assistant Engineer II |  | ORD/000260/2023-2024 | 158/AE-II/NKWSMD | 10/01/2024 | 23/07/2024 | SANTOSH TAMANG | 18.72 | 0 | 0 | 100
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/15646 | New | Proposed Gravity Based and Pumping Based PWSS for Palla Khasmahal (Mulpala part) under Lolay G.P Block: Kalimpong - II,District: Kalimpong. |  |  | BILL/00228/2024-2025 | "BP-2024-25-236 | 03/09/2024 | 03/09/2024 | WBSEDCL | 11.27 | 0 | 0 | 0
Total | [13 empty] | 228.92 | 87.32 | 38.14