## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Collection of Water Samples from different drinking water sources, tanks and reservoir etc. under Kalimpong district and submitting the same to the respective water testing laboratories (Neorakhola sub-district laboratory and Algarah sub-district laborato | SM/15669 | Support-WQMSP | COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG. | Assistant Engineer I | Junior Engineer II,Junior Engineer III | ORD/000334/2022-2023 | 2729/NKWSMD | 03/03/2023 | 03/03/2024 | NIM TSHERING LEPCHA | 25.49 | 19.52 | 76.6 | 60
Total | [13 empty] | 25.49 | 19.52 | 76.6