## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS | SM/15937 | New | Material Requisition To Resource Division |  |  | RTOR000252/2022-2023 | 2748/NKWSMD | 06/03/2023 | 06/03/2023 | Resource Division | 4.82 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS | SM/15937 | New | KUMAI KHASMAHAL & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/015530) |  |  | ORD/000336/2022-2023 | 2732/NKWSMD | 03/03/2023 | 02/03/2024 | RAMESH KUMAR AGARWAL & CO | 637.5 | 0 | 0 | 88
Total | [13 empty] | 642.32 | 0 | 0