## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG | SM/16231 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KALIMPONG G.P BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. |  |  | ORD/000053/2023-2024 | 360/NKWSMD | 26/05/2023 | 21/03/2025 | RAMESH KUMAR AGARWAL & CO | 848.05 | 474.49 | 55.95 | 80
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG | SM/16231 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 366/NKWSMD | 29/05/2023 | 29/05/2023 | Resource Division | 7.2 | 0 | 0 | 0
Total | [13 empty] | 855.25 | 474.49 | 55.48