## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16232 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 447/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 1.23 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16232 | New | WATER SUPPLY SCHEME FOR YANGMAKUM KHASMAHAL (PART-2) UNDER BLOCK KALIMPONG-I DISTRICT KALIMPONG. | Assistant Engineer I | Junior Engineer IV | ORD/000060/2023-2024 | 414/NKWSMD | 05/06/2023 | 25/05/2025 | EVERSHINE CONSTRUCTION | 376.97 | 0 | 0 | 60
Total | [13 empty] | 378.2 | 0 | 0