## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16233 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. |  |  | ORD/000070/2023-2024 | 673/NKWSMD | 12/07/2023 | 02/05/2026 | EVERSHINE CONSTRUCTION | 878.08 | 0 | 0 | 70
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16233 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 768/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 3.98 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16233 | New | Additional Work for Leftout Household in connection with Proposed Gravity Based Piped Water Supply Scheme for Paiyong Khasmahal Piped Water Supply Scheme under Kalimpong Block-II, District Kalimpong. |  |  | ORD/000377/2025-2026 | 885/NKWSMD | 18/06/2025 | 16/10/2025 | EVERSHINE CONSTRUCTION | 72.57 | 0 | 0 | 0
Total | [13 empty] | 954.63 | 0 | 0