## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16234 | New | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG-I, DISTRICT : KALIMPONG. | Assistant Engineer I,Assistant Engineer II | Junior Engineer II ,Junior Engineer III | ORD/000080/2023-2024 | 679/NKWSMD | 12/07/2023 | 18/12/2025 | DIPENDRA CHETTRI | 52.63 | 0 | 0 | 40
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16234 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 769/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 0.25 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16234 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00513/2023-2024 | BP-2023-24-319 | 17/11/2023 | 17/11/2023 | WEST BENGAL PARIVESH CAMPA | 4.74 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16234 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 07/11/2023 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
Total | [13 empty] | 63.68 | 0 | 0