## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | SM/16235 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 774/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 1.22 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | SM/16235 | New | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KAGEY G.P BLOCK : KALIMPONG-II, DISTRICT: KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000079/2023-2024 | 678/NKWSMD | 12/07/2023 | 01/07/2025 | NEOCON CONSTRUCTION CO | 208.69 | 0 | 0 | 75
Total | [13 empty] | 209.91 | 0 | 0