## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 279/NKWSMD | 17/05/2023 |  | Resource Division | 0.84 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission / Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024. | Assistant Engineer II | Junior Engineer I | ORD/000253/2023-2024 | 1468/NKWSMD | 01/12/2023 | 30/01/2024 | THE ELECTRIC SPHERE | 0.81 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG-I, DISTRICT : KALIMPONG. |  |  | ORD/000007/2023-2024 | 96/NKWSMD | 28/04/2023 | 26/08/2023 | PASANG LAMA | 156.78 | 0 | 0 | 60
Total | [13 empty] | 186.26 | 0 | 0