## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16514 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. |  |  | ORD/000051/2023-2024 | 417/NKWSMD | 05/06/2023 | 30/05/2025 | THUPDEN BHUTIA | 875.98 | 222.83 | 25.44 | 60
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16514 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 449/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 3.33 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16514 | New | PROPOSED DIVERSION OF 0.2259 HECTARES OF FOREST LAND UNDER JAL JEEVAN MISSION (JJM) SCHEME FOR GRAVITY-BASED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P. BLOCK: KALIMPONG - II |  |  | BILL/00112/2025-2026 |  | 07/07/2025 | 07/07/2025 | DIVISIONAL FOREST OFFICER | 34.32 | 0 | 0 | 0
Total | [13 empty] | 913.63 | 222.83 | 24.39