## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 277/NKWSMD | 17/05/2023 | 17/05/2023 | Resource Division | 1.95 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG-II, DISTRICT:KALIMPONG. |  |  | ORD/000009/2023-2024 | 105/NKWSMD | 28/04/2023 | 24/12/2023 | M/S. ASHOK KUMAR PERIWAL | 378.99 | 0 | 0 | 50
5 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 20 | 100
6 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 | New | PROPOSED 0.0108 HA LAND TO BE DIVERTED FOR GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAND KHASMAHAL(PART) PIPED WATER SUPPLY SCHEME |  |  | BILL/00285/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.32 | 0 | 0 | 0
Total | [13 empty] | 404.49 | 0.19 | 0.05