## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS | SM/16854 | New | WATER SUPPLY SCHEME FOR PAGRANG BONG KHASMAHAL PIPED WATER SUPPLY SCHEME GORUBATHAN BLOCK UNDER KALIMPONG DISTRICT. |  |  | ORD/000085/2023-2024 | 684/NKWSMD | 12/07/2023 | 03/11/2024 | MS. SURYA I PVT. LTD COMPANY | 388.09 | 316.1 | 81.45 | 80
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS | SM/16854 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 775/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 1.15 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS | SM/16854 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS | SM/16854 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAGRAN BONG KHASMAHAL PWSS | SM/16854 | New | PROPOSED DIVERSION OF 0.0453 HECTARES OF FOREST LAND UNDER JAL JEEVAN MISSION (JJM) SCHEME FOR GRAVITY-BASED WATER SUPPLY SCHEME BY NEORAKHOLA W/S & MTC, DIV. PHE. DTE. KALIMPONG GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PAGRANG BONG KHASMAHAL UNDER POKHARIABONG GP BLOCK: KALIMPONG -II |  |  | BILL/00287/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.32 | 0 | 0 | 0
Total | [13 empty] | 411.84 | 316.1 | 76.75