## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS | SM/18255 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 763/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 5.38 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS | SM/18255 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 23/08/2023 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS | SM/18255 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER FOR PATEN GODAK KHASMAHAL, UNDER BLOCK: GORUBATHAN, DISTRICT KALIMPONG, UNDER PUBLIC HEALTH ENGINEERING DIRECTORATE. | Assistant Engineer I,Assistant Engineer II | Junior Engineer I | ORD/000089/2023-2024 | 710/NKWSMD | 17/07/2023 | 16/07/2025 | THUPDEN BHUTIA | 1116.3 | 338.86 | 30.36 | 45
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PATEN GODAK KHASMAHAL PWSS | SM/18255 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 20 | 100
Total | [13 empty] | 1131.04 | 339.05 | 29.98