## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | SM/18322 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 771/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 6.36 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | SM/18322 | New | Continuation Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.04.2024 to 31.05.2024. | Assistant Engineer II | Junior Engineer I | ORD/000321/2023-2024 | 717/NKWSMD | 29/03/2024 | 29/05/2024 | YAMA CONSTRUCTIONS LLP | 0.39 | 0.39 | 100 | 100
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | SM/18322 | New | Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.02.2024 to 31.03.2024. | Assistant Engineer II | Junior Engineer I | ORD/000318/2023-2024 | 167/NKWSMD | 31/01/2024 | 31/03/2024 | YAMA CONSTRUCTIONS LLP | 0.39 | 0.39 | 100 | 99
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | SM/18322 | New | WATER SUPPLY SCHEME FOR ICCHA KHASAMAHAL PIPED WATER SUPPLY SCHEME IN KALIMPONG-I BLOCK, UNDER KALIMPONG DISTRICT. | Assistant Engineer II | Junior Engineer IV | ORD/000095/2023-2024 | 722/NKWSMD | 18/07/2023 | 17/07/2024 | M/S. ASHOK KUMAR PERIWAL | 920.85 | 0 | 0 | 40
Total | [13 empty] | 928 | 0.79 | 0.08