## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | SM/18415 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 957/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 2.91 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | SM/18415 | New | NIM & PHASINTING KHASMAHAL SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG |  |  | ORD/000181/2023-2024 | 945/NKWSMD | 17/08/2023 | 16/08/2025 | M/S. ASHOK KUMAR PERIWAL | 954.32 | 306.22 | 32.09 | 85
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | SM/18415 | New | (Continuation) Engagement of D.E.O (Data Entry Operator) through Agency/Contractor for Office of the Executive Engineer, Darjeeling Division-II, GTA, Kalimpong PHED for Operating proper e-Governance activity i.e.w Jal Jeevan Mission at Kalimpong, under Darjeeling Division-II Kalimpong GTA, PHE Dte. (From 01/08/2023 to 31/12/2023). |  |  | ORD/000334/2023-2024 | 30/AE-II/NKWSMD | 25/07/2023 | 25/12/2023 | RAJ BUILDERS | 0.85 | 0 | 0 | 10
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | SM/18415 | New | (Continuation) Engagement of D.E.O (Data Entry Operator) through Agency/Contractor for Office of the Executive Engineer, Darjeeling Division-II, GTA, Kalimpong PHED for Operating proper e-Governance activity i.e.w Jal Jeevan Mission at Kalimpong, under Darjeeling Division-II Kalimpong GTA, PHE Dte. (From 01/01/2024 to 31/05/2024). |  |  | ORD/000333/2023-2024 | 150/AE-II/NKWSMD | 19/12/2023 | 19/05/2024 | RAJ BUILDERS | 0.85 | 0 | 0 | 10
Total | [13 empty] | 958.94 | 306.22 | 31.93