## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | SM/18442 | Augmentation | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir / Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-II under Neorakhola Water Supply Scheme. | Assistant Engineer I | Junior Engineer IV | ORD/000238/2023-2024 | 1501/NKWSMD | 06/12/2023 | 30/11/2025 | TAJ CONSTRUCTION | 3802.55 | 472.55 | 12.43 | 25
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | SM/18442 | Augmentation | Submission of Topo Survey report, Design and Drawing of all components of the whole project including final as built drawing after being vetted by the recognised Government Institute and getting necessary approval from the Expert Committee for Augmentation of source Cum creation of spring water storage of 80ml water for improvement of and upgradation of open ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I, & Kalimpong Block-II, under Neorakhola Water Supply Scheme. | Assistant Engineer II | Junior Engineer IV | ORD/000131/2024-2025 | 2230/NKWSMD | 09/12/2024 | 08/01/2025 | THUPDEN BHUTIA | 28.69 | 0 | 0 | 100
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | SM/18442 | Augmentation | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/10/2024 TO 31/12/2024 (3 MONTHS). | Assistant Engineer I | Junior Engineer III | ORD/000120/2024-2025 | 1924/NKWSMD | 30/09/2024 | 31/12/2024 | NIM TSHERING LEPCHA | 6.36 | 0 | 0 | 100
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | SM/18442 | Augmentation | Additional work for Augmentation for source cum creation of spring water storage 80ml by improvement and improvement and upgradation of Open Ground Reservoir/Lake at 3.2 km from Algarah and all allied works to cover the uncovered area of Kalimpong Block-I and Kalimpong Block-II under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000371/2025-2026 | 859/NKWSMD | 13/06/2025 | 12/08/2025 | TAJ CONSTRUCTION | 13.16 | 0 | 0 | 0
Total | [13 empty] | 3850.76 | 472.55 | 12.27