## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1286/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 1.14 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1287/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 1.9 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1284/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 0.43 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Nimbong Khasmahal (Part) under Nimbong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000100/2023-2024 | 1091/NKWSMD | 21/09/2023 | 08/05/2024 | SANTOSH TAMANG | 166.29 | 0 | 0 | 80
5 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Lower Tunglabong, Lower Suntalay in Pokhrabong khasmahal, (Part), Pokhrabong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000105/2023-2024 | 819/NKWSMD | 24/07/2023 | 21/11/2023 | PRAKASH TAMANG | 173 | 115.65 | 66.85 | 85
6 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water SupplyScheme for Household in Jhandi Rai Goan, Chhetri Goan, Budrathoki Goan, Upper Suntalay, lower Suntalay, & Tunglabong in Pokhrabong khasmahal (Part), Pokhrabong G.P under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000109/2023-2024 | 823/NKWSMD | 24/07/2023 | 15/11/2024 | MS. SURYA I PVT. LTD COMPANY | 282.37 | 164.16 | 58.14 | 65
7 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Nechaligaon, Dangmmu Gaon & Sona Gaon, Paypang khasmahal, l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000102/2023-2024 | 818/NKWSMD | 24/07/2023 | 20/03/2024 | SITA SHARMA | 142.71 | 15.05 | 10.55 | 70
8 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Malthung Gaon, in Samthar G.P under Kalimpong Block -I in the district of Kalimpong in connection with JJM , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000232/2023-2024 | 1308/NKWSMD | 31/10/2023 | 30/12/2023 | BINOD CHANDRA BHUJEL | 23.81 | 16.85 | 70.79 | 95
9 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for 16th mile, Pagang Gumba area for left out households under Paiyong G.P under Kalimpong Block-II in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. |  |  | ORD/000008/2024-2025 | 972/NKWSMD | 18/06/2024 | 15/12/2024 | EVERSHINE CONSTRUCTION | 231.87 | 0 | 0 | 0
10 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 0.43 | 0.24 | 80
11 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in Sillery Gaon, in Paiengaon Forest village (Part), Santook G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000110/2023-2024 | 824/NKWSMD | 24/07/2023 | 13/07/2025 | JUSTINE BHUTIA | 152.07 | 0 | 0 | 45
12 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Gairi Gaon, Barmiak Thingdara, Rubasta & 10th mile Mangchu forest village, Sangsey Khashamal (Part), Sangsey G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000101/2023-2024 | 817/NKWSMD | 24/07/2023 | 13/07/2025 | M/S. ASHOK KUMAR PERIWAL | 360.01 | 0 | 0 | 56
13 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Middle & Lower Dabling, Gitdabling Khasmahal l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000107/2023-2024 | 821/NKWSMD | 24/07/2023 | 11/09/2025 | NIM TSHERING LEPCHA | 108.29 | 60.29 | 55.68 | 100
14 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in, SantookKhasmahal (Part) in Santook G.P, under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000108/2023-2024 | 822/NKWSMD | 24/07/2023 | 13/07/2025 | JUSTINE BHUTIA | 240.27 | 0 | 0 | 70
15 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in Bomfoktar Gaon, Bhujel Goan, Sunwar Goan and sorrounding areas in Samthar G.P under Kalimpong Block -I in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000231/2023-2024 | 1307/NKWSMD | 31/10/2023 | 15/02/2025 | D AND B GRACE | 39.16 | 0 | 0 | 70
16 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Manay Gumba, Cashier Gaon, MLA Gaon & Karbari Gaon, Sindibong Khasmahal (Part), Sindibong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000277/2023-2024 | 119/NKWSMD | 16/01/2024 | 31/12/2025 | SANTOSH TAMANG | 611.7 | 0 | 0 | 60
17 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in 29th mile & Galekhola under Teesta G.P under Kalimpong block-I in the district of Kalimpong connection with JJM, under Neorakhola W/S Mtc Division, P.H.E. Dte, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000009/2024-2025 | 973/NKWSMD | 18/06/2024 | 14/05/2025 | KAMAKHYA CONSTRUCTION | 172.8 | 0 | 0 | 70
18 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in Samalbongay, Suntallay, Lepcha Gaon under Samthar G.P under Kalimpong Block-I in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. |  |  | ORD/000010/2024-2025 | 974/NKWSMD | 18/06/2024 | 13/06/2025 | YADI LEPCHA | 117.35 | 18.08 | 15.41 | 80
19 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Additional work for PWS Scheme from Dhobi Khola to Kashyone G.P., Block-II Kalimpong in connection with JJM, under Neorakhola W/S & Mtc Division, PHE, Dte. | Assistant Engineer II | Junior Engineer III | ORD/000018/2024-2025 | 982/NKWSMD | 18/06/2024 | 15/12/2024 | SAINATH CONSTRUCTION COMPANY | 19.83 | 0 | 0 | 100
20 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Additional work for proposed Gravity based Piped Water Supply Scheme for Char Dhungey & Kela Busty under Pankasari Gram Panchayat under Gorubathan-II, block: Gorubathan, District: Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000102/2024-2025 | 1583/NKWSMD | 05/09/2024 | 03/05/2025 | MS JAGANNATH PRASAD | 71.24 | 0 | 0 | 50
21 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Fourteen 14 Nos of Villages (Part) Under Kalimpong Block-I & Kalimpong Block-II in The District of Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Sillary Gaon Leftout. | Assistant Engineer II | Junior Engineer IV | ORD/000021/2025-2026 | 598/NKWSMD | 29/04/2025 | 27/08/2025 | SUNIL BAJLA | 69.71 | 0 | 0 | 0
Total | [13 empty] | 3165.64 | 390.53 | 12.34