## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
2 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in Sillery Gaon, in Paiengaon Forest village (Part), Santook G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000110/2023-2024 | 824/NKWSMD | 24/07/2023 | 13/07/2025 | JUSTINE BHUTIA | 152.07 | 0 | 0 | 45
3 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Nimbong Khasmahal (Part) under Nimbong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000100/2023-2024 | 1091/NKWSMD | 21/09/2023 | 08/05/2024 | SANTOSH TAMANG | 166.29 | 0 | 0 | 80
4 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Gairi Gaon, Barmiak Thingdara, Rubasta & 10th mile Mangchu forest village, Sangsey Khashamal (Part), Sangsey G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000101/2023-2024 | 817/NKWSMD | 24/07/2023 | 13/07/2025 | M/S. ASHOK KUMAR PERIWAL | 360.01 | 0 | 0 | 56
5 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Lower Tunglabong, Lower Suntalay in Pokhrabong khasmahal, (Part), Pokhrabong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000105/2023-2024 | 819/NKWSMD | 24/07/2023 | 21/11/2023 | PRAKASH TAMANG | 173 | 115.65 | 66.85 | 85
6 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Middle & Lower Dabling, Gitdabling Khasmahal l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000107/2023-2024 | 821/NKWSMD | 24/07/2023 | 11/09/2025 | NIM TSHERING LEPCHA | 108.29 | 60.29 | 55.68 | 100
7 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water SupplyScheme for Household in Jhandi Rai Goan, Chhetri Goan, Budrathoki Goan, Upper Suntalay, lower Suntalay, & Tunglabong in Pokhrabong khasmahal (Part), Pokhrabong G.P under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000109/2023-2024 | 823/NKWSMD | 24/07/2023 | 15/11/2024 | MS. SURYA I PVT. LTD COMPANY | 282.37 | 164.16 | 58.14 | 65
8 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Nechaligaon, Dangmmu Gaon & Sona Gaon, Paypang khasmahal, l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000102/2023-2024 | 818/NKWSMD | 24/07/2023 | 20/03/2024 | SITA SHARMA | 142.71 | 15.05 | 10.55 | 70
9 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in, SantookKhasmahal (Part) in Santook G.P, under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000108/2023-2024 | 822/NKWSMD | 24/07/2023 | 13/07/2025 | JUSTINE BHUTIA | 240.27 | 0 | 0 | 70
10 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in Bomfoktar Gaon, Bhujel Goan, Sunwar Goan and sorrounding areas in Samthar G.P under Kalimpong Block -I in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000231/2023-2024 | 1307/NKWSMD | 31/10/2023 | 15/02/2025 | D AND B GRACE | 39.16 | 0 | 0 | 70
11 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Malthung Gaon, in Samthar G.P under Kalimpong Block -I in the district of Kalimpong in connection with JJM , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000232/2023-2024 | 1308/NKWSMD | 31/10/2023 | 30/12/2023 | BINOD CHANDRA BHUJEL | 23.81 | 16.85 | 70.79 | 95
12 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1286/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 1.14 | 0 | 0 | 0
13 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1287/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 1.9 | 0 | 0 | 0
14 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1284/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 0.43 | 0 | 0 | 0
15 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing piped water Supply Scheme for Household in Manay Gumba, Cashier Gaon, MLA Gaon & Karbari Gaon, Sindibong Khasmahal (Part), Sindibong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000277/2023-2024 | 119/NKWSMD | 16/01/2024 | 31/12/2025 | SANTOSH TAMANG | 611.7 | 0 | 0 | 60
16 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for 16th mile, Pagang Gumba area for left out households under Paiyong G.P under Kalimpong Block-II in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. |  |  | ORD/000008/2024-2025 | 972/NKWSMD | 18/06/2024 | 15/12/2024 | EVERSHINE CONSTRUCTION | 231.87 | 0 | 0 | 0
17 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in 29th mile & Galekhola under Teesta G.P under Kalimpong block-I in the district of Kalimpong connection with JJM, under Neorakhola W/S Mtc Division, P.H.E. Dte, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000009/2024-2025 | 973/NKWSMD | 18/06/2024 | 14/05/2025 | KAMAKHYA CONSTRUCTION | 172.8 | 0 | 0 | 70
18 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Household in Samalbongay, Suntallay, Lepcha Gaon under Samthar G.P under Kalimpong Block-I in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. |  |  | ORD/000010/2024-2025 | 974/NKWSMD | 18/06/2024 | 13/06/2025 | YADI LEPCHA | 117.35 | 18.08 | 15.41 | 80
19 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Additional work for PWS Scheme from Dhobi Khola to Kashyone G.P., Block-II Kalimpong in connection with JJM, under Neorakhola W/S & Mtc Division, PHE, Dte. | Assistant Engineer II | Junior Engineer III | ORD/000018/2024-2025 | 982/NKWSMD | 18/06/2024 | 15/12/2024 | SAINATH CONSTRUCTION COMPANY | 19.83 | 0 | 0 | 100
20 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Additional work for proposed Gravity based Piped Water Supply Scheme for Char Dhungey & Kela Busty under Pankasari Gram Panchayat under Gorubathan-II, block: Gorubathan, District: Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000102/2024-2025 | 1583/NKWSMD | 05/09/2024 | 03/05/2025 | MS JAGANNATH PRASAD | 71.24 | 0 | 0 | 50
21 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Additional Work for Proposed Surface Water Based Yakprintam Khasmahal (Part) Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kalimpong-I, Block within Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | Assistant Engineer II | Junior Engineer III | ORD/000061/2024-2025 | 1325/NKWSMD | 29/07/2024 | 25/01/2025 | RELLI PALA CONSTRUCTION | 20.76 | 0 | 0 | 100
22 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Providing Piped Water Supply Scheme for Fourteen 14 Nos of Villages (Part) Under Kalimpong Block-I & Kalimpong Block-II in The District of Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Sillary Gaon Leftout. | Assistant Engineer II | Junior Engineer IV | ORD/000021/2025-2026 | 598/NKWSMD | 29/04/2025 | 27/08/2025 | SUNIL BAJLA | 69.71 | 0 | 0 | 0
23 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Demand note for payment for Boundary pillars of the diversion of forest land against the proposed diversion of 0.0458 hectares of forestland under Jal Jeevan Mission (JJM) Scheme for GRAVITY BASED WATER SUPPLY SCHEME FOR HOUSEHOLD IN GAIRI GAON, BARMIAK THINGDARA ,RUBASTA & 10th MILE MANGCHU FOREST VILLAGE, SANGSEY KHASHMAL (PART) ,SANGSEY G.P UNDER KALIMPONG BLOCK-II IN THE DISTRICT OF KALIMPONG |  |  | BILL/00698/2024-2025 | BP-2024-25-464 | 20/01/2025 | 20/01/2025 | DIVISIONAL FOREST OFFICER | 2.07 | 0 | 0 | 0
24 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Proposed diversion of 0.0458 hectares of forestland under Jal Jeevan Misison (JJM) scheme for proposed gravity based and pumping based piped water supply scheme Gairi gaon, Barmiak Thingdara, Rubasta & 10th mile Mangchu forest village, Sangsey khashmal (part), Sangsey GP under Kalimpong block-II in the district of Kalimpong. |  |  | BILL/00288/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.77 | 0 | 0 | 0
25 | KALIMPONG | Gorubathan,Kalimpong-I,Kalimpong-II | Neorakhola W/S & Mtc.Div. | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 | New | Demand note for payment for Boundary pillars of the diverted forest land against the proposed diversion of 0.0557 hectares of forestland under Jal Jeevan Misison (JJM) scheme for proposed gravity based and pumping based piped water supply scheme for Jhandi Rai gaon, Chhetri gaon, Budrathoki gaon, Upper suntalay, Lower suntalay & Tunglabong in Pokhrabong khashmahal (part), Pokhrabong GP under Kalimpong block-II, Kalimpong |  |  | BILL/00159/2025-2026 |  | 07/08/2025 | 07/08/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.31 | 0 | 0 | 0
Total | [13 empty] | 3189.55 | 390.1 | 12.23