## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/18589 | New | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL (Part-II) PIPED WATER SUPPLY SCHEME IN KALIMPONG-II BLOCK UNDER KALIMPONG DISTRICT. |  |  | ORD/000157/2023-2024 | 891/NKWSMD | 07/08/2023 | 03/05/2025 | SRINIWAS AGARWAL | 1057.74 | 758.96 | 71.75 | 100
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/18589 | New | Demand note for payment for Boundary pillars of the diverted forest land against proposed 0.1122 ha land to be diverted Jal Jeevan Mission. (Memo No. 843/9-57/441324, Dated, Kalimpong, the 20.03.2025) |  |  | BILL/00020/2025-2026 | 78/NK/C/W/FORES | 11/07/2025 | 11/07/2025 | DIVISIONAL FOREST OFFICER | 0.46 | 0 | 0 | 0
Total | [13 empty] | 1058.21 | 758.96 | 71.72