## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | RANGO FOREST PWSS | SM/18823 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER FOR RANGO FOREST PIPED WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG, UNDER P.H.E DTE. |  |  | ORD/000203/2023-2024 | 1101/NKWSMD | 21/09/2023 | 09/12/2026 | M/S. ASHOK KUMAR PERIWAL | 1649.87 | 381.23 | 23.11 | 50
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | RANGO FOREST PWSS | SM/18823 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1173/NKWSMD | 05/10/2023 | 05/10/2023 | Resource Division | 11.65 | 0 | 0 | 0
Total | [13 empty] | 1661.53 | 381.23 | 22.94