## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | SM/19112 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 41/NKWSMD | 09/01/2024 |  | Resource Division | 4.82 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | SM/19112 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Neorakhola W/S & Mtc. Division, P.H.E. Dte. | Assistant Engineer II | Junior Engineer III | ORD/000259/2023-2024 | 157/AE-II/NKWSMD | 10/01/2024 | 25/01/2024 | SANTOSH TAMANG | 14.76 | 0 | 0 | 100
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | SM/19112 | New | DALINGKOT FOREST PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG. |  |  | ORD/000250/2023-2024 | 4/NKWSMD | 03/01/2024 | 02/01/2025 | THUPDEN BHUTIA | 1388.85 | 0 | 0 | 7
Total | [13 empty] | 1408.44 | 0 | 0