## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSER KHASMAHAL ZONE II (BHANGAY, BIMBONG) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000282/2023-2024 | 257/NKWSMD | 20/02/2024 | 13/08/2025 | KHALING ENTERPRISES | 325.39 | 0 | 0 | 45
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VI (KHARKA) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000285/2023-2024 | 260/NKWSMD | 20/02/2024 | 09/02/2026 | SUNNY CONSTRUCTION | 96.88 | 0 | 0 | 35
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE III (MALI BASSEY, KHAMDONG ) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000283/2023-2024 | 258/NKWSMD | 20/02/2024 | 14/02/2025 | SANTOSH TAMANG | 365.87 | 56.77 | 15.52 | 45
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE IV (KHARKA) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000280/2023-2024 | 255/NKWSMD | 20/02/2024 | 09/02/2026 | SUNNY CONSTRUCTION | 418.78 | 16.02 | 3.83 | 40
5 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE I (BHANGAY, SANGSER KHASMAHAL (11,12)) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000281/2023-2024 | 256/NKWSMD | 20/02/2024 | 19/02/2027 | DINESH SHERPA | 732.17 | 0 | 0 | 50
6 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VII (TARA KHOLA FOREST VILLAGE), (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000286/2023-2024 | 261/NKWSMD | 20/02/2024 | 13/08/2025 | SANTOSH TAMANG | 236.31 | 0 | 0 | 50
7 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VIII (MAN KHOLA FOREST VILLAGE), (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000287/2023-2024 | 262/NKWSMD | 20/02/2024 | 13/08/2025 | MS. SURYA I PVT. LTD COMPANY | 79.99 | 24.56 | 30.7 | 100
8 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE V (SANGSER KHASMAHAL (11,12) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000284/2023-2024 | 259/NKWSMD | 20/02/2024 | 23/08/2025 | DIPESH RAI | 170.34 | 0 | 0 | 100
9 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | (Continuation) Engagement of D.E.O (Data Entry Operator) through Agency/Contractor for Office of the Executive Engineer, Darjeeling Division-II, GTA, Kalimpong PHED for Operating proper e-Governance activity i.e.w Jal Jeevan Mission at Kalimpong, under Darjeeling Division-II Kalimpong GTA, PHE Dte. (From 01/11/2024 to 31/03/2025). |  |  | ORD/000238/2024-2025 | 139/AE-II/NKWSMD | 23/10/2024 | 23/03/2025 | RAJ BUILDERS | 0.85 | 0 | 0 | 10
10 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | (Continuation) Engagement of D.E.O (Data Entry Operator) through Agency/Contractor for Office of the Executive Engineer, Darjeeling Division-II, GTA, Kalimpong PHED for Operating proper e-Governance activity i.e.Jal Jeevan Mission at Kalimpong, under Darjeeling Division-II Kalimpong GTA, PHE Dte. (From 01/06/2024 to 31/10/2024). |  |  | ORD/000237/2024-2025 | 14/AE-II/NKWSMD | 30/05/2024 | 30/10/2024 | RAJ BUILDERS | 0.85 | 0 | 0 | 10
11 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | Additional work for water supply scheme for Sangser Khasmahal Piped Water Supply Scheme (Zone - I, II, III, IV, V, VI, VII & VIII) in Kalimpong District. (TSM/013034) under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000004/2025-2026 | 458/NKWSMD | 03/04/2025 | 30/09/2025 | MS. SURYA I PVT. LTD COMPANY | 99.75 | 0 | 0 | 0
12 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | Demand note for payment for Boundary pillars of the diverted forest land against the proposed diversion of 0.1539 hectares of forestland under Jal Jeevan Mission (JJM) Scheme for proposed gravity based and pumping based piped water supply scheme for Sangsey Khasmahal, Sangsey GP under Kalimpong Block-II in the district of kalimpong |  |  | BILL/00700/2024-2025 | BP-2024-25-465 | 20/01/2025 | 20/01/2025 | DIVISIONAL FOREST OFFICER | 5.03 | 0 | 0 | 0
13 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | Quotation as per WBSEDCL procedure-A(2010) on Turn-key/Full deposit basis Supply office: Kalimpong CCC Memo No; 4003549291/Quot/03-T.219 Supply office Address: 10th Mile, Kalimpong.,,,P.O -Kalimpong. |  |  | BILL/00690/2024-2025 | "BP-2024-25-473 | 04/02/2025 | 04/02/2025 | WBSEDCL | 13.07 | 0 | 0 | 0
14 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | Quotation as per WBSEDCL procedure-A(2010) on Turn-key/Full deposit basis Supply office: Kalimpong CCC Memo No; 4003554336/Quot/03-T.221 Supply office Address: 10th Mile, Kalimpong.,,,P.O -Kalimpong. |  |  | BILL/00689/2024-2025 | BP-2024-25-474 | 04/02/2025 | 04/02/2025 | WBSEDCL | 8.22 | 0 | 0 | 0
Total | [13 empty] | 2553.52 | 97.35 | 3.81