## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE V (SANGSER KHASMAHAL (11,12) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000284/2023-2024 | 259/NKWSMD | 20/02/2024 | 18/08/2024 | DIPESH RAI | 170.34 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VIII (MAN KHOLA FOREST VILLAGE), (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000287/2023-2024 | 262/NKWSMD | 20/02/2024 | 18/08/2024 | MS. SURYA I PVT. LTD COMPANY | 79.99 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSER KHASMAHAL ZONE II (BHANGAY, BIMBONG) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000282/2023-2024 | 257/NKWSMD | 20/02/2024 | 18/08/2024 | KHALING ENTERPRISES | 325.39 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VI (KHARKA) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000285/2023-2024 | 260/NKWSMD | 20/02/2024 | 18/08/2024 | SUNNY CONSTRUCTION | 96.88 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VII (TARA KHOLA FOREST VILLAGE), (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000286/2023-2024 | 261/NKWSMD | 20/02/2024 | 18/08/2024 | SANTOSH TAMANG | 236.31 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE III (MALI BASSEY, KHAMDONG ) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000283/2023-2024 | 258/NKWSMD | 20/02/2024 | 18/08/2024 | SANTOSH TAMANG | 365.87 | 0 | 0 | 0
7 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE IV (KHARKA) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000280/2023-2024 | 255/NKWSMD | 20/02/2024 | 18/08/2024 | SUNNY CONSTRUCTION | 418.78 | 0 | 0 | 0
8 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 | New | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE I (BHANGAY, SANGSER KHASMAHAL (11,12)) (TSM/013034) | Assistant Engineer II | Junior Engineer III | ORD/000281/2023-2024 | 256/NKWSMD | 20/02/2024 | 19/02/2025 | DINESH SHERPA | 732.17 | 0 | 0 | 0
Total | [13 empty] | 2425.74 | 0 | 0