## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI | SM/09539 | New | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 654/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.66 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI | SM/09539 | New | Piped Water Supply Scheme from Hari Khola to Upper and Lower Gumti in Samsing G.P. Gorubathan Block under Jal Swapno Programme within Kalimpong District |  |  | ORD/000065/2021-2022 | 456/NKWSMD | 14/01/2022 | 06/01/2025 | SUBAN RAI | 147.06 | 107.34 | 72.99 | 100
Total | [13 empty] | 147.73 | 107.34 | 72.66