## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2023 TO 30.04.2023. |  | Junior Engineer II | ORD/000402/2022-2023 | 2043/NKWSMD | 31/12/2022 | 30/04/2023 | QRT SECURITY AND MANPOWER SERVICE | 0.85 | 0.79 | 92.96 | 100
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.05.2023 TO 31.08.2023. |  |  | ORD/000219/2023-2024 | 126/NKWSMD | 28/04/2023 | 28/08/2023 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0.78 | 99.19 | 100
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | P.W.S SCHEME FROM GAIRIBAS KHOLA AND GEET KHOLA TO JHANDI AND ITS 20 ADJOINING VILLAGES COVERING 3 G.P (GORUBATHAN-II, NIM, POKHRAIBONG) IN GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO, DISTRICT-KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000002/2022-2023 | 9/NKWSMD | 04/04/2022 | 20/09/2024 | M/S. ASHOK KUMAR PERIWAL | 551.65 | 403.78 | 73.2 | 100
4 | KALIMPONG | Gorubathan | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | (Continuation) Hiring of vehicle for the office of Assistant Engineer under PHE,dept Kalimpong for the period of 1/10/2025 to 30/04/2026 | Assistant Engineer-III | Junior Engineer-4 | ORD/000004/2025-2026 | 462/EE/DD-II/PHE/KPG | 25/09/2025 | 24/03/2026 | MEENA CHHETRI | 0.99 | 0 | 0 | 0
5 | KALIMPONG | Gorubathan | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | Hiring of vehicle for the office of Assistant Engineer under PHE.dept Kalimpong for the period from 01/04/2025 to 01/10/2025. | Assistant Engineer-IV | Junior Engineer-2 | ORD/000001/2025-2026 | 911/EE/DD-II/PHE/KPG | 01/04/2025 | 28/09/2025 | KABITA KALIKOTAY | 0.99 | 0 | 0 | 0
6 | KALIMPONG | Gorubathan | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | Hiring of vehicle for the office of Assisstant Engineer under PHE.department kalimpong for the period from 1/04/2025 to 01/10/2025 | Assistant Engineer-III | Junior Engineer-4 | ORD/000002/2025-2026 | 909/EE/DD-II/PHE/KPG | 01/04/2025 | 28/09/2025 | MEENA CHHETRI | 0.99 | 0 | 0 | 0
7 | KALIMPONG | Gorubathan | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 | New | (Continuation) Hiring of vehicle for the office of Assistant Engineer under PHE,dept Kalimpong for the period of 1/10/2025 to 30/04/2026 | Assistant Engineer-IV | Junior Engineer-2 | ORD/000003/2025-2026 | 461/EE/DD-II/PHE/KPG | 25/09/2025 | 24/03/2026 | KABITA KALIKOTAY | 0.99 | 0 | 0 | 0
Total | [13 empty] | 557.24 | 405.35 | 72.74