## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON | SM/09542 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1377/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 0.54 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON | SM/09542 | New | P.W.S SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON AND ITS ADJOINING AREAS IN POKRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer I | Junior Engineer III | ORD/000160/2021-2022 | 889/NKWSMD | 28/03/2022 | 13/09/2024 | MS. SURYA I PVT. LTD COMPANY | 96.11 | 89.57 | 93.2 | 100
Total | [13 empty] | 96.64 | 89.57 | 92.69