## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. | SM/09544 | New | P.W.S SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI, RAI, DHAJEY GAON UNDER BHALUKHOP G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000057/2021-2022 | 448/NKWSMD | 14/01/2022 | 14/04/2022 | SUNIL BAJLA | 192.85 | 185.65 | 96.27 | 100
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. | SM/09544 | New | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 650/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.8 | 0 | 0 | 0
Total | [13 empty] | 193.65 | 185.65 | 95.87