## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON | SM/09545 | New | Details of Additional Pipeline for the work Piped Water Supply Scheme from Nimbong Khola to Upper and Lower Gashok under Nimbong Gram Panchayat. | Assistant Engineer-III | Junior Engineer-4 | ORD/000114/2023-2024 | 852/NKWSMD | 28/07/2023 | 27/08/2023 | SANTOSH TAMANG | 4.86 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON | SM/09545 | New | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 638/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.69 | 0 | 0 | 0
Total | [13 empty] | 5.55 | 0 | 0