## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING | SM/09546 | New | P.W.S SCHEME FROM MAWATAR TO UPPER DABLING UNDER GITDABLING G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000042/2021-2022 | 419/NKWSMD | 07/01/2022 | 07/04/2022 | TIKARAM SHARMA | 186.55 | 185.9 | 99.65 | 100
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING | SM/09546 | New | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 652/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.27 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING | SM/09546 | New | computer operator payment |  |  | BILL/00484/2023-2024 | BP-2023-24-193 | 30/09/2023 | 30/09/2023 | KASHYAP COMPUTERS | 0.51 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM MAWATAR TO UPPER DABLING | SM/09546 | New | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  |  | BILL/00011/2023-2024 |  | 18/04/2023 | 18/04/2023 | KASHYAP COMPUTERS | 0.85 | 0 | 0 | 0
Total | [13 empty] | 188.19 | 185.9 | 98.78