## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 | New | P.W.S SCHEME FROM OKHERBOTEY KHOLA TO UPPER PEDONG AND ITS ADJOINING AREA UNDER PEDONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000054/2021-2022 | 445/NKWSMD | 14/01/2022 | 10/09/2025 | GETEN NAMGYAL BHUTIA | 230.25 | 119.6 | 51.94 | 85
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.08.2022 to 31.01.2023 (Assistant Engineer-I). |  |  | ORD/000400/2022-2023 | 1094/NKWSMD | 29/07/2022 | 29/01/2023 | DHURBA KUMAR PRADHAN | 1.01 | 1.79 | 177.36 | 100
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.02.2022 to 31.07.2022 (Assistant Engineer-I). |  |  | ORD/000239/2021-2022 | 578/NKWSMD | 31/01/2022 | 31/07/2022 | DHURBA KUMAR PRADHAN | 1 | 2.34 | 235.51 | 100
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 | New | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 630/NKWSMD | 21/02/2022 | 21/02/2022 | Resource Division | 1.65 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.02.2023 to 30.04.2023 (Assistant Engineer-I). |  |  | ORD/000401/2022-2023 | 2254/NKWSMD | 31/01/2023 | 30/04/2023 | DHURBA KUMAR PRADHAN | 0.49 | 1.13 | 230.35 | 100
6 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 | New | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.05.2023 to 31.10.2023 (Assistant Engineer-I). |  |  | ORD/000204/2023-2024 | 111/NKWSMD | 28/04/2023 | 29/10/2023 | DHURBA KUMAR PRADHAN | 1.01 | 2.18 | 215.63 | 100
Total | [13 empty] | 235.4 | 127.05 | 53.97