## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | P.W.S SCHEME FROM SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. |  |  | ORD/000107/2021-2022 | 626/NKWSMD | 21/02/2022 | 21/07/2022 | GARGO TRADERS | 475.53 | 409.03 | 86.02 | 85
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | SUPPLEMENARY ESTIMATE OF PWS SCHEME FOR SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P., BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG. |  |  | ORD/000262/2022-2023 | 1654/NKWSMD | 04/11/2022 | 02/02/2023 | ALLIED INSTRUMENTS | 196.63 | 186.41 | 94.8 | 50
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 837/NKWSMD | 21/03/2022 | 21/03/2022 | Resource Division | 3.54 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer II ,Junior Engineer IV | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 676.65 | 595.44 | 88