## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE | SM/09594 | New | P.W.S SCHEME FROM THUKCHUK KHOLA 20TH MILE AND ITS ADJOINING AREA UNDER SAKIYONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG | Assistant Engineer I | Junior Engineer IV | ORD/000003/2022-2023 | 10/NKWSMD | 04/04/2022 | 16/08/2025 | THUPDEN BHUTIA | 740.54 | 582.85 | 78.71 | 70
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE | SM/09594 | New | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 1370/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 2.96 | 0 | 0 | 0
Total | [13 empty] | 743.5 | 582.85 | 78.39