## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM UNEAK KHOLA TO DABLING | SM/09595 | New | P.W.S. Scheme from Uneak Khola to Dabling and its adjoining area under Gitdabling G.P. Block II under Kalimpong under Jal Swapno Programme within Darjeeling |  |  | ORD/000046/2021-2022 | 425/NKWSMD | 07/01/2022 | 07/04/2022 | YAMA CONSTRUCTIONS LLP | 123.23 | 0 | 0 | 100
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM UNEAK KHOLA TO DABLING | SM/09595 | New | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 658/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.52 | 0 | 0 | 0
Total | [13 empty] | 123.75 | 0 | 0