## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | SM/09596 | New | Hiring of vehicle (bolero) no. WB-79B-0359 of daily hire basis for the office of the Executive Engineer Kalimpong Division, PHE Department. W.E.F 01/02/2022 TO 01/02/2023 |  |  | ORD/000001/2021-2022 | 962/EE/DDII/PHE/GTA | 27/01/2022 | 27/01/2023 | AVASH RAI | 2.15 | 0 | 0 | 100
2 | KALIMPONG | Kalimpong-I | Darjeeling Division II (Kalimpong) | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | SM/09596 | New | Hiring of vehicle (bolero) no. WB-74BJ-6606 of daily hire basis for the office of the Executive Engineer Kalimpong Division, PHE Department. | Assistant Engineer-III | Junior Engineer-3 | ORD/000002/2021-2022 | 963/EE/DD-II/PHE/GTA | 27/01/2022 | 27/01/2023 | SARASWATI SINGH | 2.15 | 0 | 0 | 100
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | SM/09596 | New | P.W.S SCHEME FROM DHATURAY JHORA TO DEWRALI GAON, GUMBA GAON AND BICH GAON AREA UNDER KAFFER-KANKEBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000109/2021-2022 | 625/NKWSMD | 21/02/2022 | 21/07/2022 | SANTOSH TAMANG | 305.11 | 0 | 0 | 100
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | SM/09596 | New | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 836/NKWSMD | 21/03/2022 | 21/03/2022 | Resource Division | 1.76 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | SM/09596 | New | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 1369/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 1.76 | 0 | 0 | 0
Total | [13 empty] | 312.94 | 0 | 0