## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON | SM/09598 | New | P.W.S. Scheme from Okherbotay Jhora to Dara Gaon Lower Burmek under Munsung G.P. Block II Kalimpong under Jal Jeevan Mission and Jal Swapno Programme |  |  | ORD/000047/2021-2022 | 426/NKWSMD | 07/01/2022 | 07/04/2022 | DINESH SHERPA | 93.5 | 0 | 0 | 100
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON | SM/09598 | New | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 639/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.31 | 0 | 0 | 0
Total | [13 empty] | 93.81 | 0 | 0