## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. | SM/09599 | New | P.W.S SCHEME FROM DHOBI KHOLA TO KASHYONE AND ITS ADJOINING AREA UNDER KASHYONE G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000110/2021-2022 | 627/NKWSMD | 21/02/2022 | 21/07/2022 | DINESH SHERPA | 302.88 | 0 | 0 | 80
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. | SM/09599 | New | Material Requisition To Resource Division |  |  | RTOR000035/2021-2022 | 838/NKWSMD | 21/03/2022 | 21/03/2022 | Resource Division | 2.76 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. | SM/09599 | New | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 1380/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 2.76 | 0 | 0 | 0
Total | [13 empty] | 308.4 | 0 | 0