## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | SM/09600 | New | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 636/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 1.29 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | SM/09600 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | SM/09600 | New | Piped Water Supply Scheme from Sisney and Ankurey Jhora to Nokdara and its adjoining area under Lava- Gitbeong G.P. Block ll, Kalimpong under Jal Swapno Programme within Kalimpong District |  |  | ORD/000067/2021-2022 | 458/NKWSMD | 14/01/2022 | 14/04/2022 | DIPESH RAI | 162.74 | 0 | 0 | 80
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | SM/09600 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
Total | [13 empty] | 192.34 | 0 | 0