## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | SM/09601 | New | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 647/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 1.35 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | SM/09601 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 07/11/2023 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | SM/09601 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | SM/09601 | New | Piped Water Supply Scheme from Chamung Khola to Gitdabling Bazar and adjoining area under Gitdabling G.P. Block ll Kalimpong under Jal Swapno Programme within Kalimpong District |  |  | ORD/000050/2021-2022 | 429/NKWSMD | 07/01/2022 | 19/05/2025 | SITA SHARMA | 196.23 | 88.49 | 45.09 | 100
5 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | SM/09601 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 216.19 | 88.49 | 40.93