## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | Pws scheme from 7th Mile Jhora to Algarah | SM/09602 | New | P.W.S SCHEME FROM 7TH MILE TO ALGARAH BAZAR UNDER SANTOOK G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer I | Junior Engineer IV | ORD/000108/2021-2022 | 622/NKWSMD | 21/02/2022 | 06/01/2025 | JUSTINE BHUTIA | 297.77 | 235.28 | 79.01 | 80
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | Pws scheme from 7th Mile Jhora to Algarah | SM/09602 | New | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 833/NKWSMD | 21/03/2022 | 21/03/2022 | Resource Division | 2.48 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | Pws scheme from 7th Mile Jhora to Algarah | SM/09602 | New | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 1375/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 2.77 | 0 | 0 | 0
Total | [13 empty] | 303.02 | 235.28 | 77.65