## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE | SM/09606 | New | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 645/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 1.26 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE | SM/09606 | New | P.W.S. Scheme from Bheri Posher Khola to Kothi Line via 6 nos. village in Nim G.P. Gorubathan Block under Lal Jeevan Mission and Jal Swapno Programme |  |  | ORD/000048/2021-2022 | 427/NKWSMD | 07/01/2022 | 13/09/2024 | M/S R.S. CONSTRUCTION | 192.09 | 174.94 | 91.07 | 100
Total | [13 empty] | 193.36 | 174.94 | 90.47