## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN | SM/09607 | New | Piped Water Supply Scheme from Bhupaley Khola to Paren and and its surrounding area in Paren Godak G.P. Gorubathan Block Kalimpong, under Jal Swapno Programme within Kalimpong District |  |  | ORD/000062/2021-2022 | 453/NKWSMD | 14/01/2022 | 14/04/2022 | RAMESH KUMAR AGARWAL & CO | 105.63 | 74.3 | 70.34 | 85
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN | SM/09607 | New | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 656/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 1.14 | 0 | 0 | 0
Total | [13 empty] | 106.77 | 74.3 | 69.59